## 22-134 Socket.
Plan [ Time std ] | Topic | In-charge | Progress | Start Date | End Date | Time | Delay plan | Status | Privote | Remark.
Maker Process : Tooling / Mold
20 Weeks. = 140 Days. | Mold design ( 3D ) & Design confirm | Unipro. | 100% | 2024-12-16 | 2024-12-22 | 6d |  | Complete | o
^ | Purchase material & Standard part | Unipro. | 100% | 2024-12-16 | 2024-12-22 | 6d |  | Complete | o
^ | Manufacture | Unipro. | 100% | 2025-01-01 | 2025-01-20 | 19d |  | Complete | o
^ | Assembly & Fitting | Unipro. | 100% | 2025-01-21 | 2025-01-27 | 6d |  | Complete | o
^ | Trial production. | Unipro. | 100% | 2025-01-28 | 2025-01-31 | 3d |  | Complete | o
| Summary |  |  |  |  | 40d
Home line trial - Stage ( Mass production mold )
^ | T0 Buid condition. | Unipro. | 100% | 2025-01-28 | 2025-01-31 | 3d |  | Complete | o
^ | T0 Part review | Unipro. | 20% | 2025-02-01 | 2025-02-16 | 15d |  | In Progress | o
^ | T1 Build condition | Unipro. | 0% | 2025-02-17 | 2025-02-24 | 7d |  | Not Started | o
12 Weeks. = 84 days. | Testing & Evaluation | Unipro | 0% | 2025-02-17 | 2025-03-03 | 14d |  | Not Started | o
| Summary |  |  |  |  | 39d
MCP : New part process
4 Weeks. = 30 Days. | Drawing request create from PSD | VE , PSD | 0% | 2025-02-05 | 2025-03-07 | 30d |  | Not Started | o
1 Week. = 7 Days | Meeting & issue ES . | VE | 0% | 2025-02-17 | 2025-02-20 | 3d |  | Not Started | o
20 Weeks. = 140 Days. | Parts sample request | VE , Unipro | 0% | 2025-02-10 | 2025-02-17 | 7d |  | Not Started | o
^ | Inspection new parts. | QA | 0% | 2025-02-24 | 2025-03-10 | 14d |  | Not Started | o
12 Weeks. = 84 Days. | Installing workability | VE , DC2 | 0% | 2025-02-24 | 2025-03-10 | 14d |  | Not Started | o
^ | Water tightness | VE , QA , Unipro | 0% | 2025-02-24 | 2025-03-10 | ^ |  | Not Started | o
^ | Heat cycle | VE , QA , Unipro | 0% | 2025-02-24 | 2025-03-10 | ^ |  | Not Started | o
^ | Adhesion | VE , QA , Unipro | 0% | 2025-02-24 | 2025-03-10 | ^ |  | Not Started | o
^ | Fitting check. [ Leak test. ] | VE , QA , Unipro | 0% | 2025-02-24 | 2025-03-10 | ^ |  | Not Started | o
37 Weeks. 258 Days. | Summary |  |  |  |  | 68d
Test Report.
2 Weeks. = 14 days. | -Inspection new parts. | QA | 0% | 2025-03-01 | 2025-03-15 | 14d |  | Not Started | o
2 Weeks. = 14 days. | -Installing workability | DC2 | 0% | 2025-03-01 | 2025-03-15 | 14d |  | Not Started | o
^ | -Water tightness | Unipro | 0% | 2025-03-01 | 2025-03-15 | 14d |  | Not Started | o
^ | -Heat cycle | Unipro | 0% | 2025-03-01 | 2025-03-15 | ^ |  | Not Started | o
^ | -Adhesion | Unipro | 0% | 2025-03-01 | 2025-03-15 | ^ |  | Not Started | o
^ | -Fitting check. [ Leak test. ] | Unipro | 0% | 2025-03-01 | 2025-03-15 | ^ |  | Not Started | o
2 Weeks. = 14 days. | Summary |  |  |  |  | 14d
| Audit process at UNIPRO. | QA , PUR | 0% | 2025-03-24 | 2025-03-31 | 7d |  | Not Started | o
| Summary data for issue document for approved. | VE | 0% | 2025-03-24 | 2025-03-31 | 7d |  | Not Started | o
| Issue document to MELSHI for request approve mass prod. | VE | 0% | 2025-03-24 | 2025-03-31 | 7d |  | Not Started | o
| MELSHI Judgement and reply. | VE | 0% | 2025-04-01 | 2025-04-16 | 15d |  | Not Started | o
| Clear stock current part. | VE | 0% | 2025-04-18 | 2025-05-01 | 13d |  | Not Started | o
| Mass prod. | VE | 0% | 2025-06-01 | 30/06/2025 | 30d |  | Not Started | o